## Sheet1
Team Rescue Robot Task Plan
Date：
No | Caleb Damilola |  |  |  | No | Johnson Kwabena Darko |  |  |  |  | No | Ali Ahmed
| To do | Deadline | Done | Taking Task from someone |  | To do | Deadline | Done | Taking Task from Someone | Done |  | To do | Deadline | Done | Taking Task from someone
1 | Requirement Diagram | 17-04-21 | 16-04-21 |  | 1 | Activity Diagram | 17-04-21 | 16-04-21 | Excel file preparation | 22-04-21 | 1 | Task Excel file | 17-04-21
2 | System Context Diagram | 23-04-21 | 22-04-21 |  | 2 | Use Case Diagram | 23-04-21 | 22-04-21
[7 empty] | 23-04-21 | 22-04-21